## Sheet1
User Story |  |  | Sprint 1 |  | 12 hours total | 4 hr/person
Product backlog | Priority | estimate (Story point) | Task | Priority | Estimate Hours) | Who | Doing | Done
QnA feature | 2 | Large | Create the HTML for recurring icons | 1 | 2 | Abeer
Map feature | 2 | Small | Create template header in HTML | 1 | 1 | Justin
Search feature | 3 | Medium | Create template divider (Content) in HTML | 1 | 1 | Justin
Messaging system feature | 3 | Medium | Create template footer in HTML | 1 | 1 | Abeer
Create a study group feature | 1 | Large | Create the interactable map in HTML | 2 | 2 | Jack
Create final designs on figma | 1 | Medium | Create the CSS for each of the recurring icons | 3 | 2 | Justin
|  |  | Create the CSS for the interactable map | 3 | 2 | Jack
|  |  | Create HTML for question asking page | 2 | 1 | Abeer